## Slide 1: UAT testing for Partners

## Slide 2: Overview
UAT overview
Typical issues during UAT
Tips - Before UAT
Tips - During UAT
Acceptance
Bug prioritization
Test management - X-Ray overview

## Slide 3: UAT overview for customer
Goals for UAT testing:
  Test E2E process in real environment - Pricefx software together with CRM, ERP and other software you use for pricing
  Check that Pricefx software does what it should to support your business
  Move the project to live, start using it and let it help to your business
UAT testing is not:
  Repeating tests from Feature Sprints
  Time for submitting change requests
  Time for getting know the application
Your responsibility before and during UAT:
  Create UAT test cases and test according to those test cases on QA partition
  Report founded bugs to JIRA or other tool based on your choice
  Accept the solution so development phase can be formally finished

## Slide 4: UAT overview
Timing:
  you will have 2 weeks to test all your UAT test scenarios
  2 weeks are enough for testing, but testers must be prepared and test every day for a while (at least 2 or 3 hours)
  It’s impossible to do the whole testing in one day, please, be ready for that
  Limited time frame means organized approach is needed
Expected documentation:
  Test cases for UAT
    help to testers to be clear about what must be tested during UAT
    give to testers possibility to organize time for testing and discuss unclear things before UAT
  Reporting of test results
    Managers have an overview of where testers are in the process of testing what still must be tested
    Testers know what they already tested so they can organize their testing
  Bugs in JIRA or other tool based on your choice
    Correct bug reporting will speed-up fixing process

## Slide 5: Typical issues during UAT
No plan for UAT testing
  testers are doing exploratory testing
  UAT testing is not under control
  Time expected for UAT testing is usually not sufficiant
  It‘s not possible to monitor the progress
  Problems with accepting the solution – UAT testers always want to test more
No priorities of test cases
  Critical issues are reported at the end of UAT
No training for UAT testers
  reported bugs are not bugs but questions, change requests or misunderstandings
  UAT testers are learning how to work with Pfx application instead of testing
UAT testers don‘t have time for testing
  UAT testers are not testing because they are doing other work, they should have time dedicated for UAT

## Slide 6: Tips - Before UAT
Select group of UAT testers
  Usually SMEs – check with them that tey will have time for testing
  Make sure they have access to all systems they need for UAT
Create UAT test cases
  Based on business cases, they should cover end to end scenarios
  Should contain at least check lists of what should be verified
Choose UAT leader
  Somebody from the project team who knows the solution
  UAT testers are reporting results to him/her
Choose test management tool
  It is possible to use X-Ray in Pricefx Jira (see below), or other tool based on your choice. Note: Excel is not a test management tool
Training of UAT tester – application and UAT process
  Demo session with all UAT testers to show them how to use developed sw and clarify expectations from UAT testing
  Let testers check the functionality for themselves and help them with first issues and questions
  It‘s useful when demo is done based on UAT test cases and the session is recorded

## Slide 7: Tips - During UAT
Testing according to UAT test cases
  UAT testers should have Test execution (if X-Ray is used)
  Test cases should be prioritized so critical functionality is verified at the beginning of UAT
  Keep in mind there is limited time for UAT phase, there is no time to retest everything from Feature Sprints
Report test results
  UAT testers should log test results every day
  Important part of test results are attached screens and description of what was tested
Report bugs in Jira or other tool based on your choice
  Issue Type = „Bug“ (if the selected tool is Jira)
  Reported bug should contain description of the issue, expected result and screens or other useful files
Retest all fixes
  Close the bug and finish testing of the UAT test case
Check the progress of testing every day
  UAT Leader should check the progress every day to see if somebody from UAT testers has good progress in testing

## Slide 8: Acceptance
Acceptance after UAT testing means we can continue to Go-Live and using the solution in production
There is no reason for not accepting because of medium and low bugs, they can be fixed after Go-Live during Stabilization phase
There is time frame for UAT phase on the project, decision should be made at the end of this time frame

## Slide 9: Bug prioritization
Prioritization of bugs:
  note: the example is from JIRA, but similar prioritization can be used also in other tool
Priority | Explanation
Critical | User is unable to use the Solution, resulting in a critical impact on business operations. This condition requires immediate resolution. Example: system is down.
High | Any high priority defect which is incorrect price calculation. No workaround is available, and the defect is time sensitive. Example: defect is blocking pricing from being exported to ERP systems.
Medium | The defect requires attention but does not block pricing. A workaround is available but may not be optimal. Example: a defect requires the user to perform manual calculations.
Low | Minor loss of functionality. These may be monitoring issues, clarifications, documentation questions; or administrative tasks. Example: update the column label or any other cosmetic related defects.

## Slide 10: Test management – X-Ray overview
X-Ray – test management plug-in in JIRA
No additional cost for the project
Test documentation and results of testing are visible for our project team and for the customer
Test cases are in separate issue types, not in Comments section
Test cases are linked to user stories, so it is clear why they were created and what they test
Can be used for Feature Sprint and UAT testing
Easy to use for everybody who is familiar with JIRA
JIRA functionalities available (exports, imports, workflows, …)
Used on projects by Pricefx since 04/2021
Used by customers for UAT since 10/2021

## Slide 11: Test management - details
Test cases are visible in Testing Board