## Actions
RAID LOG
Project name: |  |  |  |  | Project ID:
Project manager: |  |  |  |  | Project Sponsor:
ACTIONS
Action No: | Date raised | Area | Priority | Description | Action by | Deadline | Progress | Status
1 | dd/mm/yyyy | Marketing console | Medium | PM to contact the product team and report back on: known bugs and max mailing volume. | Project Manager | dd/mm/yyyy | Product team are compiling a list which they will send to us end of this month. | Pending

## Risks
RISKS
Risk No. | Date Identified | Description | Probability | Impact | Preventative Actions | Contingent Actions | Owner | Actions by | Target Date | Status | Notes
1 |  | There is a risk of delays and errors as the customisations are developed through the portal rather than LMS. | Medium | High | Ensure training completed by project kick off. | Use LMS rather than the portal for the initial phase. | Project Manager | Project Manager |  | Open

## Issues
Issues
Issue No. | Priority | Description | Owner | Cause | Resolution | Status | Comments | Target date
1 | Medium | Customisation library needs to be revised to make it compatible with new version. |  | Compability between products. | Update library to be compatible with new version. | Pending | Developers are assessing work involved. He will report back on…....

## Decisions
Decisions
Decision no: | Date made | Description | Impact | Approver/decision maker | Evidence e.g. Email date and title
1 |  | Note that the 12 languages are excluded from the upgrade. Project Manager to ensure this is noted in SoW and Project Charter. | Customer do not expect the languages to be included, but may be expecting us do some planning during the upgrade project. | Project Sponsor | Noted in meeting planning meeting actions dated…..

## Dropdowns
Dropdowns
To change menu items simply edit the Menu and Description fields below.
Actions
Field | Menu | Description
Priority | High | Complete in 1 - 2 days
| Medium | Complete in 1 week
| Low | Complete in 1 to 2 weeks
Status | Open | In progress
| Pending | Waiting on action by another party
| Resolved | Resolved pending agreement from customer/sponsor
| Closed | Closed as agreed by customer/sponsor
Risks
Field | Menu | Description
Probability | High | Very likely that this risk will occur/happen.
| Medium | 50/50 chance that this risk will occur.
| Low | Low probability that this risk will occur.
Impact | High | This would badly impact the project e.g. cost, delay, quality.
| Medium | A manageable impact on the project.
| Low | A low impact on the project.
Status | Open | In progress
| Pending | Waiting on action by another party
| Closed | Closed as agreed by customer/sponsor
Issues
Field | Menu | Description
Priority | High | This issue must be resolved for progress to be made.
| Medium | This impacts the project, but doesn’t stop progress.
| Low | A low impact on the project. Perhaps optional to fix.
Status | Open | In progress
| Pending | Waiting on action by another party
| Resolved | Resolved pending agreement from customer/sponsor
| Closed | Closed as agreed by customer/sponsor

## Useful resources
Project Management resources
Project Management Templates
The Top 50 Business Risks (and how to manage them)!
Issue Log Template [free download]
End Project Report Template
Risk Register Template
Stakeholder Management Templates
Work Breakdown Structure (WBS) template in Excel