## Risks
RISKS
Risk No. | Date Identified | Description | Probability | Impact | Preventative Actions | Contingent Actions | Owner | Actions by | Target Date | Status | Notes
1 |  | There is a risk of delays and errors as the customisations are developed through the portal rather than LMS. | Medium | High | Ensure training completed by project kick off. | Use LMS rather than the portal for the initial phase. | Project Manager | Project Manager |  | Open

## Actions
RAID LOG
Project name: |  |  |  |  | Project ID:
Project manager: |  |  |  |  | Project Sponsor:
ACTIONS
Action No: | Date raised | Area | Priority | Description | Action by | Deadline | Progress | Status
1 | dd/mm/yyyy | Marketing console | Medium | PM to contact the product team and report back on: known bugs and max mailing volume. | Project Manager | dd/mm/yyyy | Product team are compiling a list which they will send to us end of this month. | Pending

## Issues
Issues
Issue No. | Priority | Description | Owner | Cause | Resolution | Status | Comments | Target date
1 | Medium | Customisation library needs to be revised to make it compatible with new version. |  | Compability between products. | Update library to be compatible with new version. | Pending | Developers are assessing work involved. He will report back on…....

## Decisions
Decisions
Decision no: | Date made | Description | Impact | Approver/decision maker | Evidence e.g. Email date and title
1 |  | Note that the 12 languages are excluded from the upgrade. Project Manager to ensure this is noted in SoW and Project Charter. | Customer do not expect the languages to be included, but may be expecting us do some planning during the upgrade project. | Project Sponsor | Noted in meeting planning meeting actions dated…..