## User Stories
User Stories |  | Project ID: | C4DRM
Story No. | Epic | Story Name | As a… | I want to… | So I can… | Acceptance Criteria | Notes | Priority | Sprint | Owner
1 | Identification | Identify Business Data Stewards | Pricing DIrector | identify the Business process owners/stewards | have them identify which business processes are associated with pricing data | - a single person is identified as the owner/steward for each Business Process associated with pricing data - each identified person certifies that the business process is capable of providing pricing data when requested - the business owners/stewards names are documented in the "Data Source Template"
2 | Identification | Identify Business Processes | Business Steward | identify which Business processes are associated with pricing data | ensure each process is capable of providing all required pricing data needed to support the pricing effort | - each business process involved with creating pricing data is identified - the business processes are documented in the "Data Source Template" | Include some detail about how to delineate a business process? For example, price setting may be one, but there could be more than one for different types of quoting, etc.
3 | Identification | Identify IT Data Stewards | Pricing Director | identify the IT Data Stewards | have them identify which IT systems, databases, processes and tools are associated with pricing data | - a single person is identified as the owner/steward for each IT System associated with pricing data - each identified person certifies that the IT system is capable of providing pricing data when requested - the IT owners/stewards names are documented in the "Data Source Template"
4 | Identification | Identify IT Systems | IT Data Steward | identify which IT systems, databases, processes and tools are associated with creating pricing data | ensure each system is available to provide all required pricing data needed to support the pricing effort | - all critical data elements can be sourced within the organization - each IT system involved with creating pricing data is identified and documented in the "Data Source Template"
5 | Availability | Identify and Mitigate Data Delivery Risks | Data Readiness Manager | Work with the Business and IT Data Stewards, along with the Project Manager to identify risks associated with the delivery of data | mitigate data delivery risks | - A Risk Log is created, updated and maintained on an agreed to frequency
6 | Availability | Establish and Maintain the Data Delivery Timeline | Data Readiness Manager | Work with the Business and IT Data Stewards, along with the Project Manager to establish and maintain the data delivery timeline | best estimate the start of Feature Sprint #1 | - Data delivery timeline is created and agreed to by the Customer Project Manager
7 | Identification | Scoping: Identify Critical Business Process Data Elements | Business and IT Data Steward | catalog the critical data elements in my business process | understand what data will need to be brought in to support the process | - The business data elements for each scoped business process have been identified - Completion of the <Business Processes> tabs in the "Data Scoping Document" | This item is part of the scoping phase
8 | Identification | Scoping: Complete Data Entity Definition | Business and IT Data Steward | provide a completed data scoping document to Pricefx | enable Pricefx to effectively build a Pricefx data model | - Completion of the <Data Entities> tab in the "Data Scoping Document" - Agreement that the "Data Scoping Document" is complete | This would conclude the scoping phase and the result here should be a completed scoping document.
9 | Identification | Integration: Identify and review data integration and security standards | Pricing project team | identify and understand any data management/integration standards that must be followed | establish integrations with Pricefx that adhere to organization protocols and security requirements | - Discuss and resolve any data exchange processes and concepts that must be adhered to - Acquire any permissions or authorizations needed to exchange data with Pricefx - Complete any pre-work that needs to be done to allow internal systems to communcate with Pricefx servers | The focus of this story includes firewalls, data security and messaging standards, IT snd tandards for integration
10 | Availability | Integration: Determine Data Integration Design | Pricing project team | create a plan for exporting and importing data to and from Pricefx | maintain accurate and updated data in the Pricefx system | - Decide how each in-scope source system will be integrated with Pricefx
11 | Availability | Provide Sample Data (Iterative) | Business and IT Data Steward | provide a representative sample of my organization's data to the Pricefx team | insure that the Pricefx data model and system data meet the needs of my business processes | - Provide sample data for each extract / table that will be used in the system | This iterative activity is part of the modeling phase Document each extract/table that is to be used in Pricefx
12 | Identification | Complete Data Specification Document | Pricefx Solution Architect | complete the data integration specification document | proceed with the build out of the data model and integration interfaces | - Define each interface and all parameters in the specification document - Create a mapping tab for each interface in the Data Specification document | This item is part of the modeling phase
13 | Quality | Communicate Data Element Definitions | Data Readiness Manager | ensure the Business and IT Data Stewards, and the Pricefx team understand the data element definitions so as to define quality data | prepare the Business and IT Data Stewards to be able to provide quality data | - all involved acknowledge they understand the data element definitions.
14 | Quality | Define the Data Quality Check process | Data Readiness Manager | ensure the Project Team understands the Data Quality Check process, including the inputs and outputs | execute the data quality check process efficiently with the Business and IT Data Stewards | - all involved acknowledge they understand the Data Quality Check process, inputs and outputs
15 | Quality | Perform Data Quality Check (Iterative) | Data Readiness Manager | ensure the "Master" data provided by the Business and IT Data Stewards meets the Pricefx quality standards | Upload the "master" data into the Pricefx system. | - a data quality score of ___% has been achieved

## JIRA Upload Template
Story_No | Epic Name | Story Name | As a(n)… | I want to… | So I can… | Notes | Project | Story_Name_Full | Description | Acceptance Criteria | Priority
1 | Identification | Identify Business Data Stewards | Pricing DIrector | identify the Business process owners/stewards | have them identify which business processes are associated with pricing data | 0 | C4DRM | 1. Identify Business Data Stewards | As a(n) Pricing DIrector, I want to identify the Business process owners/stewards so I can have them identify which business processes are associated with pricing data. | - a single person is identified as the owner/steward for each Business Process associated with pricing data - each identified person certifies that the business process is capable of providing pricing data when requested - the business owners/stewards names are documented in the "Data Source Template"
2 | Identification | Identify Business Processes | Business Steward | identify which Business processes are associated with pricing data | ensure each process is capable of providing all required pricing data needed to support the pricing effort | Include some detail about how to delineate a business process? For example, price setting may be one, but there could be more than one for different types of quoting, etc. | C4DRM | 2. Identify Business Processes | As a(n) Business Steward, I want to identify which Business processes are associated with pricing data so I can ensure each process is capable of providing all required pricing data needed to support the pricing effort. Notes: Include some detail about how to delineate a business process? For example, price setting may be one, but there could be more than one for different types of quoting, etc. | - each business process involved with creating pricing data is identified - the business processes are documented in the "Data Source Template"
3 | Identification | Identify IT Data Stewards | Pricing Director | identify the IT Data Stewards | have them identify which IT systems, databases, processes and tools are associated with pricing data | 0 | C4DRM | 3. Identify IT Data Stewards | As a(n) Pricing Director, I want to identify the IT Data Stewards so I can have them identify which IT systems, databases, processes and tools are associated with pricing data. | - a single person is identified as the owner/steward for each IT System associated with pricing data - each identified person certifies that the IT system is capable of providing pricing data when requested - the IT owners/stewards names are documented in the "Data Source Template"
4 | Identification | Identify IT Systems | IT Data Steward | identify which IT systems, databases, processes and tools are associated with creating pricing data | ensure each system is available to provide all required pricing data needed to support the pricing effort | 0 | C4DRM | 4. Identify IT Systems | As a(n) IT Data Steward, I want to identify which IT systems, databases, processes and tools are associated with creating pricing data so I can ensure each system is available to provide all required pricing data needed to support the pricing effort. | - all critical data elements can be sourced within the organization - each IT system involved with creating pricing data is identified and documented in the "Data Source Template"
5 | Availability | Identify and Mitigate Data Delivery Risks | Data Readiness Manager | Work with the Business and IT Data Stewards, along with the Project Manager to identify risks associated with the delivery of data | mitigate data delivery risks | 0 | C4DRM | 5. Identify and Mitigate Data Delivery Risks | As a(n) Data Readiness Manager , I want to Work with the Business and IT Data Stewards, along with the Project Manager to identify risks associated with the delivery of data so I can mitigate data delivery risks. | - A Risk Log is created, updated and maintained on an agreed to frequency
6 | Availability | Establish and Maintain the Data Delivery Timeline | Data Readiness Manager | Work with the Business and IT Data Stewards, along with the Project Manager to establish and maintain the data delivery timeline | best estimate the start of Feature Sprint #1 | 0 | C4DRM | 6. Establish and Maintain the Data Delivery Timeline | As a(n) Data Readiness Manager , I want to Work with the Business and IT Data Stewards, along with the Project Manager to establish and maintain the data delivery timeline so I can best estimate the start of Feature Sprint #1. | - Data delivery timeline is created and agreed to by the Customer Project Manager
7 | Identification | Scoping: Identify Critical Business Process Data Elements | Business and IT Data Steward | catalog the critical data elements in my business process | understand what data will need to be brought in to support the process | This item is part of the scoping phase | C4DRM | 7. Scoping: Identify Critical Business Process Data Elements | As a(n) Business and IT Data Steward, I want to catalog the critical data elements in my business process so I can understand what data will need to be brought in to support the process. Notes: This item is part of the scoping phase | - The business data elements for each scoped business process have been identified - Completion of the <Business Processes> tabs in the "Data Scoping Document"
8 | Identification | Scoping: Complete Data Entity Definition | Business and IT Data Steward | provide a completed data scoping document to Pricefx | enable Pricefx to effectively build a Pricefx data model | This would conclude the scoping phase and the result here should be a completed scoping document. | C4DRM | 8. Scoping: Complete Data Entity Definition | As a(n) Business and IT Data Steward, I want to provide a completed data scoping document to Pricefx so I can enable Pricefx to effectively build a Pricefx data model. Notes: This would conclude the scoping phase and the result here should be a completed scoping document. | - Completion of the <Data Entities> tab in the "Data Scoping Document" - Agreement that the "Data Scoping Document" is complete
9 | Identification | Integration: Identify and review data integration and security standards | Pricing project team | identify and understand any data management/integration standards that must be followed | establish integrations with Pricefx that adhere to organization protocols and security requirements | The focus of this story includes firewalls, data security and messaging standards, IT snd tandards for integration | C4DRM | 9. Integration: Identify and review data integration and security standards | As a(n) Pricing project team, I want to identify and understand any data management/integration standards that must be followed so I can establish integrations with Pricefx that adhere to organization protocols and security requirements. Notes: The focus of this story includes firewalls, data security and messaging standards, IT snd tandards for integration | - Discuss and resolve any data exchange processes and concepts that must be adhered to - Acquire any permissions or authorizations needed to exchange data with Pricefx - Complete any pre-work that needs to be done to allow internal systems to communcate with Pricefx servers
10 | Availability | Integration: Determine Data Integration Design | Pricing project team | create a plan for exporting and importing data to and from Pricefx | maintain accurate and updated data in the Pricefx system | 0 | C4DRM | 10. Integration: Determine Data Integration Design | As a(n) Pricing project team, I want to create a plan for exporting and importing data to and from Pricefx so I can maintain accurate and updated data in the Pricefx system. | - Decide how each in-scope source system will be integrated with Pricefx
11 | Availability | Provide Sample Data (Iterative) | Business and IT Data Steward | provide a representative sample of my organization's data to the Pricefx team | insure that the Pricefx data model and system data meet the needs of my business processes | This iterative activity is part of the modeling phase Document each extract/table that is to be used in Pricefx | C4DRM | 11. Provide Sample Data (Iterative) | As a(n) Business and IT Data Steward, I want to provide a representative sample of my organization's data to the Pricefx team so I can insure that the Pricefx data model and system data meet the needs of my business processes. Notes: This iterative activity is part of the modeling phase Document each extract/table that is to be used in Pricefx | - Provide sample data for each extract / table that will be used in the system
12 | Identification | Complete Data Specification Document | Pricefx Solution Architect | complete the data integration specification document | proceed with the build out of the data model and integration interfaces | This item is part of the modeling phase | C4DRM | 12. Complete Data Specification Document | As a(n) Pricefx Solution Architect, I want to complete the data integration specification document so I can proceed with the build out of the data model and integration interfaces. Notes: This item is part of the modeling phase | - Define each interface and all parameters in the specification document - Create a mapping tab for each interface in the Data Specification document
13 | Quality | Communicate Data Element Definitions | Data Readiness Manager | ensure the Business and IT Data Stewards, and the Pricefx team understand the data element definitions so as to define quality data | prepare the Business and IT Data Stewards to be able to provide quality data | 0 | C4DRM | 13. Communicate Data Element Definitions | As a(n) Data Readiness Manager , I want to ensure the Business and IT Data Stewards, and the Pricefx team understand the data element definitions so as to define quality data so I can prepare the Business and IT Data Stewards to be able to provide quality data . | - all involved acknowledge they understand the data element definitions.
14 | Quality | Define the Data Quality Check process | Data Readiness Manager | ensure the Project Team understands the Data Quality Check process, including the inputs and outputs | execute the data quality check process efficiently with the Business and IT Data Stewards | 0 | C4DRM | 14. Define the Data Quality Check process | As a(n) Data Readiness Manager , I want to ensure the Project Team understands the Data Quality Check process, including the inputs and outputs so I can execute the data quality check process efficiently with the Business and IT Data Stewards. | - all involved acknowledge they understand the Data Quality Check process, inputs and outputs
15 | Quality | Perform Data Quality Check (Iterative) | Data Readiness Manager | ensure the "Master" data provided by the Business and IT Data Stewards meets the Pricefx quality standards | Upload the "master" data into the Pricefx system. | 0 | C4DRM | 15. Perform Data Quality Check (Iterative) | As a(n) Data Readiness Manager , I want to ensure the "Master" data provided by the Business and IT Data Stewards meets the Pricefx quality standards so I can Upload the "master" data into the Pricefx system.. | - a data quality score of ___% has been achieved
0 | 0 | 0 | 0 | 0 | 0 | 0 | C4DRM
0 | 0 | 0 | 0 | 0 | 0 | 0 | C4DRM
0 | 0 | 0 | 0 | 0 | 0 | 0 | C4DRM
0 | 0 | 0 | 0 | 0 | 0 | 0 | C4DRM
0 | 0 | 0 | 0 | 0 | 0 | 0 | C4DRM
0 | 0 | 0 | 0 | 0 | 0 | 0 | C4DRM
0 | 0 | 0 | 0 | 0 | 0 | 0 | C4DRM
0 | 0 | 0 | 0 | 0 | 0 | 0 | C4DRM
0 | 0 | 0 | 0 | 0 | 0 | 0 | C4DRM
0 | 0 | 0 | 0 | 0 | 0 | 0 | C4DRM
0 | 0 | 0 | 0 | 0 | 0 | 0 | C4DRM
0 | 0 | 0 | 0 | 0 | 0 | 0 | C4DRM
0 | 0 | 0 | 0 | 0 | 0 | 0 | C4DRM